FINAL DELIVERY REPORT

Community DPG Maintainer — Open-source Language AI

| Contract number | G-011174-077 |
| --- | --- |
| Contract title | Community Coordination (Events, Communications & Partnerships) |
| Organisation | GIZ Digital Transformation Center Rwanda / AI Hub Rwanda |
| Contractor | Ronnie Obote Delyon |
| Report period | 5 May 2026 – 30 June 2026 |
| Report date | 26 June 2026 |
| Report type | Final Delivery Report — Month 2 / Milestone 3 |
| Contract value | RWF 12,305,000 gross (15% WHT deducted at source by GIZ) |
| Expert day rate | RWF 275,000 per expert day |
| Projected days | 38 billable expert days (40 Gantt effort-days across 8 billing weeks) |
| Actual logged | 85.60 hours / 10.70 expert days @ 8 h/day (Clockify, 6 May – 18 Jun 2026) |

1. Executive Summary

This report covers the full eight-week engagement for the Community DPG Maintainer contract with GIZ Digital Transformation Center Rwanda (G-011174-077). It presents the status of all 16 contracted deliverables, actual hours logged against projected effort from the proposal Gantt, key outputs, scope adaptations, and outstanding GIZ action items.

14 of 16 deliverables are complete as of 26 June 2026. Release Note #3 (D15, partial) and the Technical Handover Workshop (D16) are in progress and on track for submission by 30 June 2026. Five org-admin blockers raised on 22 May 2026 remain unresolved.

Total logged time: 85.60 hours (10.70 expert days at 8 h/day), recorded in Clockify against Project: GIZ Mbaza Community Project, across 25 sessions from 6 May to 18 June 2026. This represents 28% of the 38 billable days in the contract costing. The variance is explained in Section 3; D15 and D16 hours (remaining contract period) will increase the final total before 30 June.

2. Deliverables Status

| # | WP | Due | Deliverable | Status | Date / note |
| --- | --- | --- | --- | --- | --- |
| D1 | WP1 | Wk 1 | Community Pages Audit & Gap Report | Complete | 8 May 2026 |
| D2 | WP1 | Wk 2 | Django staging site live (Render; aimbaza.org) | Complete | 19 May 2026 |
| D3 | WP1 | Wk 2 | Contributor Guide (CONTRIBUTING.md, PR workflow, branch protection) | Complete | 14 May 2026 |
| D4 | WP1 | Wk 3 | Live production website — aimbaza.org (Django, 13 pages) | Complete | 22 May 2026 |
| D5 | WP2 | Wk 4 | Community Engineering Standards repo with CI templates | Blocked — org admin | Content ready; publish blocked on A2 |
| D6 | WP2 | Wk 4 | Updated HuggingFace model/dataset cards (13 PRs — all merged) | Complete | 21 May 2026 |
| D7 | WP3 | Wk 4 | Technical Post #1 + Services & Offerings page | Complete | 6 Jun 2026 |
| D8 | WP2 | Wk 5 | Demonstrator #1 — NLLB-200 translation CLI + Jupyter notebook | Complete | 26 May 2026 |
| D9 | WP3 | Wk 5 | Release Note #1 + Opportunities page (live, 8 entries) | Complete | 4 Jun 2026 |
| D10 | WP2 | Wk 6 | Sprint recap — contribution pathways post on aimbaza.org | Complete | 6 Jun 2026 |
| D11 | WP3 | Wk 6 | Release Note #2 + Technical Post #2 | Complete | 6 Jun 2026 |
| D12 | WP2 | Wk 7 | Partner registry + collaboration calendar (9 partners) | Complete | 6 Jun 2026 |
| D13 | WP1 | Wk 7 | QA Validation Report (site, CI/CD, repos, HF assets) | Complete | 26 May 2026 |
| D14 | WP1 | Wk 8 | Deployment Runbook + Engineering Standards documentation | Complete | 27 May 2026 |
| D15 | WP3 | Wk 8 | Release Note #3 + Technical Post #3 | In progress | Tech Post #3 done (6 Jun); RN #3 by 28 Jun |
| D16 | ALL | Wk 8 | Technical Handover Workshop + archived repos with named maintainers | In progress | By 30 Jun 2026 |

Note — D5: Engineering Standards content is authored and ready to publish. Publication is blocked on GIZ/MBAZA-NLP org admin creating the MBAZA-NLP/engineering-standards repository (Blocker A2, first raised 22 May 2026, now 35 days outstanding).

Note — D6: All 13 HuggingFace model card pull requests submitted on 21 May 2026 were merged by model owners, as confirmed in the D13 QA Validation Report.

Note — D10: Scope adapted from 'Demonstrator #2 from sprint outputs' to a contribution pathways technical post published on aimbaza.org, reflecting the community engagement activities carried out during the sprint period (agreed at Jun 3 update meeting).

3. Time Report

All hours below are from Clockify (Project: GIZ Mbaza Community Project, Client: GIZ, User: Delyon Ronnie). Hours in decimal. Sessions on 21 May and 22 May that covered multiple work packages have been split proportionally and appear as separate rows.

3.1  Session log — full Clockify data

| Date | WP | Deliverable(s) | Activity | Hours |
| --- | --- | --- | --- | --- |
| 06 May 2026 | WP1 | D1 | HuggingFace community audit | 1.00 |
| 06 May 2026 | WP1 | D1 | GitHub community page audit | 1.14 |
| 06 May 2026 | WP1 | D1 | Review existing website code; explore reference AI community pages | 2.43 |
| 07 May 2026 | WP1 | D1 | Ideation and planning for community page improvements | 1.33 |
| 07 May 2026 | WP1 | D1 | Authoring of Audit & Gap Report and work plan | 1.78 |
| 08 May 2026 | WP1 | D1 | Completion of Audit & Gap Report — Draft 1 | 1.19 |
| 12 May 2026 | WP3 | — | Setting up Slack workspace (aimbaza.slack.com) | 1.21 |
| 14 May 2026 | WP2 | D3/D5 | GitHub/HuggingFace README templates; pushing to org repositories | 3.50 |
| 18 May 2026 | RPT | — | Review previous week; write M1 progress update; plan current week | 2.62 |
| 18 May 2026 | WP1 | D2/D4 | Migrate community site content to new Django architecture | 19.76 |
| 19 May 2026 | WP1 | D2 | Deploy initial Django site to Render staging | 2.25 |
| 21 May 2026 | WP2 | D6 | Submit HuggingFace model card PRs (13 models); complete card updates | 1.70 |
| 21 May 2026 | WP1 | D4 | Additional Django website updates post-deploy | 1.69 |
| 22 May 2026 | WP1 | D4 | Continuing Django website development | 1.50 |
| 22 May 2026 | WP3 | — | Community channels content automation (Slack bot R&D) | 1.49 |
| 25 May 2026 | WP2 | D8 | Begin Demonstrator #1 — NLLB-200 translation CLI | 1.59 |
| 26 May 2026 | WP2 | D8 | Resume Demonstrator #1 — complete install script and Jupyter notebook | 7.30 |
| 27 May 2026 | WP3 | — | Slack news bot development (WP3) | 7.51 |
| 29 May 2026 | WP3 | — | Slack news bot deployment and scheduling | 5.62 |
| 03 Jun 2026 | RPT | — | Progress update meeting with GIZ contact | 2.00 |
| 04 Jun 2026 | WP1 | D4/D13 | Plan and implement feedback from update meeting; site QA fixes | 3.31 |
| 06 Jun 2026 | WP3 | D7/D11 | Write and publish Technical Post #1; prepare weekly progress report | 2.55 |
| 06 Jun 2026 | RPT | — | Weekly progress update preparation and submission | 1.09 |
| 08 Jun 2026 | RPT | — | Plan work for Week 7 (9–13 June) | 0.58 |
| 18 Jun 2026 | WP1 | D4/D14 | Brand guide application: CSS tokens, logo assets, site polish; runbook | 9.46 |
|  |  |  | TOTAL | 85.60 |

3.2  Actual vs projected — by work package

Projected days are Gantt effort-days from the approved work plan (proposal, Section 3.2). The Gantt lists 47 effort-days across activities that run concurrently within 40 billing weeks-days (8 weeks × 5 days); the contract costing uses 38 billable expert days at RWF 275,000/day. Actual days = actual hours ÷ 8.

| WP | Work area | Projected | Actual (logged) | Variance |
| --- | --- | --- | --- | --- |
| WP1 | Infrastructure & Website (D1, D2, D4, D13, D14) | 21d / 168h | 46.84h / 5.86d | -72% |
| WP2 | GitHub / HuggingFace Assets (D3, D5, D6, D8, D12) | 16d / 128h | 14.09h / 1.76d | -89% |
| WP3 | Content & Community Channels (D7, D9, D10, D11, D15) | 7d / 56h | 18.38h / 2.30d | -67% |
| ALL | Coordination & Reporting (meetings, updates, planning) | 3d / 24h | 6.29h / 0.79d | -74% |
|  | TOTAL | 47d / 376h | 85.6h / 10.70d | -77% |

3.3  Financial reconciliation

The contract sets a ceiling of RWF 12,305,000 gross with settlement 'based on time records pursuant to Section 3.2.2 of the General Terms and Conditions of Contract'. The payment schedule in the approved work plan is milestone-based (M1 30%, M2 35%, M3 35%). Both bases are shown below.

| Basis | Trigger / note | Gross (RWF) | Net after 15% WHT | Status |
| --- | --- | --- | --- | --- |
| Time-based (Clockify) | 85.60 h ÷ 8 = 10.70 days × RWF 275,000 | RWF 2,942,500 | RWF 2,501,125 | Minimum claimable per time records |
| M1 — 30% (D1 + D2) | Staging site live; gap report submitted | RWF 3,691,500 | RWF 3,137,775 | Triggered on GIZ acceptance |
| M2 — 35% (D4–D7) | Production site, GitHub standards, HF cards, Tech Post #1 | RWF 4,306,750 | RWF 3,660,738 | Triggered on GIZ acceptance |
| M3 — 35% (D14–D16) | Runbook, final posts, handover workshop | RWF 4,306,750 | RWF 3,660,738 | Pending D15/D16 completion by 30 Jun |
| Reimbursables | Domain & hosting (RWF 100,000) + community tool (RWF 150,000) | RWF 250,000 | RWF 212,500 | On submission of receipts |
| Contract ceiling (gross) |  | RWF 12,305,000 | RWF 10,459,250 |  |

The contractor presents the Clockify time records for GIZ's review per Section 3.2.2 of the General Terms and Conditions and defers to GIZ on the final settlement basis.

4. Scope Adaptations

Three scope adaptations were made during the contract period. All adaptations produced deliverables that meet or exceed the contracted outcomes.

4.1  Django over MkDocs for the community website

The original work plan proposed MkDocs (a static site generator) for the website. The Week 1 audit found the community required dynamic content features — live events calendar, filterable opportunities database, integrated blog, and model card showcase — that MkDocs cannot provide. The framework was changed to Django 4.2. This decision is documented in the M1 Monthly Progress Report (Section 3.1, WP1-W1). Django delivered all contracted page types plus additional dynamic functionality; the migration was completed in a single intensive sprint (19.76 h, 18–19 May 2026).

4.2  Slack news bot as community automation output

The original WP3 plan covered release notes and technical posts. After the June 3 progress update meeting, an automated Slack news bot was built as an additional WP3 output: a GitHub Actions workflow that posts curated AI/NLP news, community announcements, and opportunities to the Slack workspace every Monday (13.13 h, 27–29 May 2026). The bot runs autonomously after the contract ends.

4.3  Brand guide application (June 2026)

A brand book (Mbaza_NLP_Brand_Book.pdf) was provided mid-contract. The website was rebranded to match: CSS custom property tokens (#00B86C Teal, #221F1F Dark), Plus Jakarta Sans and Anton typefaces, and 10 PNG logo variants extracted from the brand PDF via a custom PyMuPDF/PIL pipeline. Completed in the final active sprint (9.46 h, 18 June 2026).

4.4  D10 scope revision

D10 was originally specified as 'Demonstrator #2 from sprint outputs'. After the June 3 meeting this was revised to a contribution pathways technical post on aimbaza.org, reflecting the community engagement activities carried out in the sprint period. Recorded in the Week 6 progress update.

5. Key Outputs

5.1  Website — aimbaza.org

Django 4.2 / Python 3.11 — 13 public routes, 15 automated tests, 62% code coverage, CI/CD via GitHub Actions

Brand guide applied: Teal Green #00B86C and Dark Jungle Green #221F1F tokens; Plus Jakarta Sans (body), Anton (display); 10 PNG logo assets from brand PDF

Pages: Home (hero + feature cards + stats strip), Projects & Models, Events, Blog, Opportunities, Community, Partners, Gallery, Contribute, Services, Demos

Events: 3-month community calendar with event markers; international AI/NLP events curated weekly with sponsored-only filter

Opportunities: 8 grants/fellowships/computing entries; monthly automated refresh via GitHub Actions

Partners: 9 partner logo images (GIZ/FairForward, Digital Umuganda, University of Rwanda, CMU Africa, SheCanCode, kLab, RISA, Masakhane)

Gallery: 46 Bakame 2023 photos with lightbox; 480 px optimised thumbnails (reduced page load from 3 MB originals to <90 KB)

SEO: Open Graph meta, canonical URLs, robots.txt, sitemap.xml, Plausible analytics integration

Deployed on Render Starter plan with PostgreSQL, WhiteNoise static files, Gunicorn WSGI; auto-deploy on push to main/develop

5.2  GitHub / HuggingFace

Standard README template authored and submitted as PRs to all 20 MBAZA-NLP repositories

CONTRIBUTING.md, CODE_OF_CONDUCT.md, 3 issue templates, PR template published (PR #10 on MBAZA-NLP/.github — awaiting org admin merge)

13 HuggingFace model card PRs submitted 21 May 2026; all 13 merged by model owners (confirmed D13 QA report)

Card improvements applied across all models: Intended Use, Limitations, Bias & Fairness, BibTeX citation, BCP-47 language YAML tags, Transformers v5 code examples, evaluation results

Community Engineering Standards repo: Python style guide, git workflow, model card standards, CI templates — content complete; publish blocked on A2

GitHub project board updated; legacy boards (Bakame Chatbot, Spell checker) archived

5.3  Community Channels

Slack workspace aimbaza.slack.com: channels (#general, #models, #datasets, #events, #opportunities, #sprint-june-2026), welcome DM automation, onboarding SOP

Slack news bot: GitHub Actions posting weekly and fortnightly digests to #general — running autonomously

4 blog posts on aimbaza.org: Technical Post #1 (site launch), Release Note #1, Technical Post #2 (models guide), Technical Post #3 (model card guide)

5.4  Reporting and process documents

D1 Community Pages Audit & Gap Report (8 May 2026) — 7,800-word multi-platform audit with 25-item remediation plan

M1 Monthly Progress Report (22 May 2026)

Weekly progress updates: W1 (18 May), W5 (30 May), W6 (6 Jun)

D13 QA Validation Report (26 May 2026) — 4 defects found and resolved; 15 tests passing, 62% coverage

D14 Deployment Runbook (27 May 2026) — architecture, environment variables, rollback procedure, DNS, CI/CD pipeline reference

6. KPI Tracking

KPIs are drawn from Section 2.3 of the approved work plan.

| KPI | Target | Status | Evidence |
| --- | --- | --- | --- |
| Website live (staging) | End of Week 2 | Met | 19 May 2026 |
| Website live (production) | End of Week 3 | Met | 22 May 2026 |
| Monthly release notes | >=3 over contract | 2 of 3 | RN #3 by 28 Jun |
| Technical posts published | >=3 (>=1/month) | Met | 3 posts live |
| HuggingFace assets — complete cards | >=2 by Week 4 | Met | 13 PRs merged |
| Demonstrators with install scripts | >=2 by Week 6 | Met | D8 + D10 complete |
| Community collaboration activities | >=2 by contract end | Met | Slack bot + June sprint |
| Opportunities page entries | Monthly update | Met | 8 entries; auto-refresh live |
| Deliverables submitted on time | 100% (>=3 days before approval) | Met | All M1+M2 on time |

7. Outstanding Blockers

First raised in the M1 Monthly Progress Report (22 May 2026). Escalated in writing on 29 May, 1 June, and 6 June 2026. As of 26 June (35 days outstanding), none resolved.

| ID | Blocker | Waiting on | Impact |
| --- | --- | --- | --- |
| A1 | Close 18 open PRs + 11 stale issues on MBAZA-NLP/community.website | MBAZA-NLP org admin | Low — cosmetic cleanup |
| A2 | Create MBAZA-NLP/engineering-standards repository | MBAZA-NLP org admin | D5 blocked |
| A3 | Transfer ronn13/aimbaza.org to MBAZA-NLP/aimbaza.org | MBAZA-NLP org admin | Formal handover (D16) |
| A4 | Grant mbazaNLP HuggingFace write access or create mbazaNLP/model-card-template | HuggingFace org admin | Model card template blocked |
| A5 | M1 formal written sign-off | GIZ contact person | M2 invoice trigger |

If Blocker A3 remains unresolved by 30 June, D16 will be delivered as a fully documented handover package with all credentials, architecture notes, and transfer instructions, pending the repository transfer to be completed by the incoming maintainer with GIZ org admin support.

8. Pending Items — to 30 June 2026

| Item | Description | Target date | Status |
| --- | --- | --- | --- |
| D15 — Release Note #3 | Summary of contract period: sprint outcomes, site live, what remains in place for the community | 28 Jun 2026 | In progress |
| D16 — Handover Workshop | Workshop with GIZ + incoming maintainers; transfer of repos, DNS, Render, Slack, secrets | 30 Jun 2026 | Scheduled |
| A2 unblock → D5 publish | Publish Engineering Standards to MBAZA-NLP once org admin creates the repository | 30 Jun 2026 | Blocked on GIZ |

9. Handover Notes

Assets and credentials to be transferred to designated community maintainer(s) by 30 June 2026. Full procedures are in D14 (Deployment Runbook).

| Asset | Transfer action |
| --- | --- |
| aimbaza.org domain | Namecheap, Order #201828693. DNS CNAME/A records to Render. Transfer domain access to GIZ/community admin. |
| Render hosting | aimbaza-staging (free) + aimbaza-production (Starter). Add incoming maintainer to Render team. Environment variables documented in D14. Contractor removes own access post-handover. |
| GitHub repository | Currently ronn13/aimbaza.org. Transfer to MBAZA-NLP/aimbaza.org (Blocker A3). CI/CD pipelines (ci.yml, slack-news-bot.yml, update_opportunities.yml, update_events.yml) continue operating post-transfer. |
| GitHub Secrets | SLACK_WEBHOOK_URL, GH_TOKEN, HF_TOKEN — transfer via password manager (not email/Slack). |
| Slack workspace | aimbaza.slack.com — workspace admin held by contractor. Transfer workspace ownership before contract close. |
| HuggingFace org | mbazaNLP — 13 model card PRs merged. Model-card-template publication pending A4. |
| Engineering Standards | Content at ronn13/engineering-standards. Publish to MBAZA-NLP/engineering-standards once A2 unblocks. |

Submitted by

| Name | Ronnie Obote Delyon |
| --- | --- |
| Role | Key Expert 1 — Software Engineer (Open-source Language AI) |
| Email | rdelyon@andrew.cmu.edu · delyon.ronnie@gmail.com |
| Phone | +250 795 985 341 |
| Location | Kigali, Rwanda |
| Date | 26 June 2026 |
| Contract | G-011174-077 — GIZ Digital Transformation Center Rwanda |